## Sheet1
| Task Name | Duration (Weeks) | Predecessor
| Stage 1 |  |  | Stage 1 Total Weeks | 30
A | Scope | 2 |  | Stage 2 Total Weeks | 18
B | Initial Analysis | 1 | A | Stage 3 Total Weeks | 18
C | Project Plan | 1 | B
D | System Analysis | 2 | C
E | System Design | 2 | D
F | Season Module | 10 | E | 22
G | Results and Ladder Module | 10 | E
H | Testing | 2 | F G
Stage 2
I | Web Analysis | 3 | H
J | Web Design | 3 | I |  | 56
K | Web Implementation | 10 | J
L | Web Testing | 2 | K
Stage 3
M | Mobile Analysis | 3 | L
N | Mobile Design | 3 | M
O | Mobile Implementation | 10 | N
P | Mobile Testing | 2 | O